## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Advanced Analytics Project | 24 days? | August 16, 2017 8:00 AM | September 18, 2017 5:00 PM |  | 0 | To be used as a template - dates are not accurate.
1 | Yes | Auto Scheduled | Project Kickoff | 1 day? | August 16, 2017 8:00 AM | August 16, 2017 5:00 PM |  | 1 | The Team Data Science Process (TDSP) provides a recommended lifecycle that you can use to structure the development of your data science projects. The lifecycle outlines the steps, from start to finish, that projects usually follow when they are executed.
2 | Yes | Auto Scheduled | Business Understanding | 8 days? | August 17, 2017 8:00 AM | August 28, 2017 5:00 PM | 1 | 1 | Goals...
3 | Yes | Auto Scheduled | Define Objectives | 1 day? | August 17, 2017 8:00 AM | August 17, 2017 5:00 PM | 1 | 2 | Work with your customer and other stakeholders to understand and identify the business problems. Formulate questions that define the business goals and that data science techniques can target.
4 | Yes | Auto Scheduled | Identify the key business variables | 1 day? | August 18, 2017 8:00 AM | August 18, 2017 5:00 PM | 3 | 2 | A central objective of this step is to identify the key business variables that the analysis needs to predict. These variables are referred to as the model targets and the metrics associated with them are used to determine the success of the project. Two
5 | Yes | Auto Scheduled | Define Project Goals | 1 day? | August 18, 2017 8:00 AM | August 18, 2017 5:00 PM | 3 | 2 | Define the project goals by asking and refining "sharp" questions that are relevant and specific and unambiguous. Data science is the process of using names and numbers to answer such questions. ...
6 | Yes | Auto Scheduled | Define project team | 1 day? | August 18, 2017 8:00 AM | August 18, 2017 5:00 PM | 3 | 2 | Define the project team by specifying the roles and responsibilities of its members. Develop a high-level milestone plan that you iterate on as more information is discovered.
7 | Yes | Auto Scheduled | Define success metrics | 1 day? | August 21, 2017 8:00 AM | August 21, 2017 5:00 PM | 6 | 2 | Define success metrics. For example: Achieve customer churn prediction accuracy of X% by the end of this 3-month project, so that we can offer promotions to reduce churn. The metrics must be SMART: ...
8 | Yes | Auto Scheduled | Identify Data Sources | 5 days? | August 22, 2017 8:00 AM | August 28, 2017 5:00 PM | 7 | 2 | Identify data sources that contain known examples of answers to your sharp questions. Look for the following data:...
9 | Yes | Auto Scheduled | Data Sources Documented | 0 days | August 28, 2017 5:00 PM | August 28, 2017 5:00 PM | 8 | 2 | This is the Raw Data Sources section of the Data Definitions report that is found in the TDSP project Data Report folder here: https://github.com/Azure/Azure-TDSP-ProjectTemplate/blob/master/Docs/DataReport/Data%20Defintion.md#raw-data-sources. It specifi
10 | Yes | Auto Scheduled | Data Dictionaries Delivered | 0 days | August 28, 2017 5:00 PM | August 28, 2017 5:00 PM | 9 | 2 | This document provides descriptions of the data that is provided by the client. These descriptions include information about the schema (data types, information on validation rules, if any) and the entity-relation diagrams if available. The Azure Data Cat
11 | Yes | Auto Scheduled | Charter Document Delivered | 0 days | August 28, 2017 5:00 PM | August 28, 2017 5:00 PM | 10 | 2 | A standard template is provided here: https://github.com/Azure/Azure-TDSP-ProjectTemplate/blob/master/Docs/Project/Charter.md. ...
12 | Yes | Auto Scheduled | Data Acquisition and Understanding | 7 days? | August 29, 2017 8:00 AM | September 6, 2017 5:00 PM | 11 | 1 | Goals: ...
13 | Yes | Auto Scheduled | Ingest the data | 3 days? | August 29, 2017 8:00 AM | August 31, 2017 5:00 PM | 11 | 2 | Set up the process to move the data from source locations to the target locations where analytics operations like training and predictions are to be executed.
14 | Yes | Auto Scheduled | Explore the data | 3 days? | September 1, 2017 8:00 AM | September 5, 2017 5:00 PM | 13 | 2 | Before you train your models, you need to develop a sound understanding of the data. Real-world datasets are often noisy or are missing values or have a host of other discrepancies. Data summarization and visualization can be used to audit the quality of
15 | Yes | Auto Scheduled | Set up data pipeline | 1 day? | September 6, 2017 8:00 AM | September 6, 2017 5:00 PM | 14 | 2 | In addition to the initial ingestion and cleaning of the data, you typically need to set up a process to score new data or refresh the data regularly as part of an ongoing learning process. This can be done by setting up a data pipeline or workflow. ...
16 | Yes | Auto Scheduled | Deliver Data Quality Report | 0 days | September 5, 2017 5:00 PM | September 5, 2017 5:00 PM | 14 | 2 | This report contains data summaries, relationships between each attribute and target, variable ranking etc. The IDEAR tool provided as part of TDSP can quickly generate this report on any tabular dataset such as a CSV file or a relational table: https://g
17 | Yes | Auto Scheduled | Deliver a Solution Architecture | 0 days | September 5, 2017 5:00 PM | September 5, 2017 5:00 PM | 16 | 2 | This can be a diagram or description of your data pipeline used to run scoring or predictions on new data once you have built a model. It also contains the pipeline to retrain your model based on new data. The document is stored in the Project directory w
18 | Yes | Auto Scheduled | Checkpoint Decision | 0 days | September 5, 2017 5:00 PM | September 5, 2017 5:00 PM | 17 | 2 | Before you begin full feature engineering and model building, you can reevaluate the project to determine whether the value expected is sufficient to continue pursing it. You may, for example, be ready to proceed, need to collect more data, or abandon the
19 | Yes | Auto Scheduled | Modeling | 6 days? | September 6, 2017 8:00 AM | September 13, 2017 5:00 PM | 17 | 1 | Goals:...
20 | Yes | Auto Scheduled | Feature Engineering | 1 day? | September 6, 2017 8:00 AM | September 6, 2017 5:00 PM | 18 | 2 | Feature engineering involves inclusion, aggregation and transformation of raw variables to create the features used in the analysis. If you want insight into what is driving a model, then you need to understand how features are related to each other and h
21 | Yes | Auto Scheduled | Train Model | 1 day? | September 7, 2017 8:00 AM | September 7, 2017 5:00 PM | 20 | 2 | Depending on type of question you are trying answer, there are many modeling algorithms available. The process for model training includes the following steps: ...
22 | Yes | Auto Scheduled | Evaluate Model | 1 day? | September 8, 2017 8:00 AM | September 8, 2017 5:00 PM | 21 | 2 | Evaluate (training and test dataset) a series of competing machine learning algorithms along with the various associated tuning parameters (known as parameter sweep) that are geared toward answering the question of interest with the current data
23 | Yes | Auto Scheduled | Define Feature Sets | 1 day? | September 11, 2017 8:00 AM | September 11, 2017 5:00 PM | 22 | 2 | The features developed for the modeling are described in the Feature Sets section of the Data Definition report. It contains pointers to the code to generate the features and description on how the feature was generated....
24 | Yes | Auto Scheduled | Create Model Report | 1 day? | September 12, 2017 8:00 AM | September 12, 2017 5:00 PM | 23 | 2 | For each model that is tried, a standard, template-based report that provides details on each experiment is produced....
25 | Yes | Auto Scheduled | Checkpoint Decision | 1 day? | September 13, 2017 8:00 AM | September 13, 2017 5:00 PM | 24 | 2 | Evaluate whether the model is performing well enough to deploy it to a production system. Some key questions to ask are:...
26 | Yes | Auto Scheduled | Deployment | 1 day? | September 14, 2017 8:00 AM | September 14, 2017 5:00 PM | 25 | 1 | Models with a data pipeline are deployed to a production or production-like environment for final user acceptance.
27 | Yes | Auto Scheduled | Operationalize the Model | 1 day? | September 14, 2017 8:00 AM | September 14, 2017 5:00 PM | 25 | 2 | Once you have a set of models that perform well, they can be operationalized for other applications to consume. Depending on the business requirements, predictions are made either in real-time or on a batch basis. To be operationalized, the models have to
28 | Yes | Auto Scheduled | Deliver status dashboard | 0 days | September 14, 2017 5:00 PM | September 14, 2017 5:00 PM | 27 | 2 | Create a status dashboard of system health and key metrics
29 | Yes | Auto Scheduled | Deliver final modeling report | 0 days | September 14, 2017 5:00 PM | September 14, 2017 5:00 PM | 28 | 2 | Create a final modeling report with deployment details.
30 | Yes | Auto Scheduled | Deliver Final solution architecture document | 0 days | September 14, 2017 5:00 PM | September 14, 2017 5:00 PM | 29 | 2 | Create a final solution architecture document.
31 | Yes | Auto Scheduled | Customer Handoff | 2 days? | September 15, 2017 8:00 AM | September 18, 2017 5:00 PM | 30 | 1 | Goal: Finalize the project deliverables: confirm that the pipeline, the model, and their deployment in a production environment are satisfying customer objectives.
32 | Yes | Auto Scheduled | System Validation | 1 day? | September 15, 2017 8:00 AM | September 15, 2017 5:00 PM | 30 | 2 | The customer should validate that the system meets their business needs and the answers the questions with acceptable accuracy to deploy the system to production for use by their client application. All the documentation is finalized and reviewed.
33 | Yes | Auto Scheduled | Project Handoff | 1 day? | September 18, 2017 8:00 AM | September 18, 2017 5:00 PM | 32 | 2 | A hand-off of the project to the entity responsible for operations is completed. This could be, for example, an IT or customer data science team or an agent of the customer that is responsible for running the system in production.
34 | Yes | Auto Scheduled | Project Close-out: Exit Report of Project for Customer | 0 days? | September 18, 2017 5:00 PM | September 18, 2017 5:00 PM | 33 | 2 | The main artifact produced in this final stage is the Exit Report of Project for Customer. This is the technical report containing all details of the project that useful to learn about and operate the system. An Exit Report template is provided by TDSP th

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Business | Bz | Work |  |  |  |  | 100% | $0.00/h | 0
2 | IT Director | Di | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Data Engineer | De | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Data Scientist | Ds | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Front End Developer | Fe | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Visualization | Vi | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Tester | Te | Work |  |  |  |  | 100% | $0.00/h | 0
8 | DevOps | Do | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Project Kickoff | Business | 0 | 8h | 100%
Project Kickoff | Data Scientist | 0 | 8h | 100%
Project Kickoff | DevOps | 0 | 8h | 100%
Business Understanding | Business | 0 | 64h | 100%
Business Understanding | Data Scientist | 0 | 64h | 100%
Define Objectives | Business | 0 | 8h | 100%
Identify the key business variables | Business | 0 | 8h | 100%
Identify the key business variables | Data Scientist | 0 | 8h | 100%
Identify the key business variables | Data Engineer | 0 | 8h | 100%
Define Project Goals | Business | 0 | 8h | 100%
Define Project Goals | Data Scientist | 0 | 8h | 100%
Define Project Goals | IT Director | 0 | 8h | 100%
Define project team | IT Director | 0 | 8h | 100%
Define success metrics | IT Director | 0 | 8h | 100%
Define success metrics | Business | 0 | 8h | 100%
Define success metrics | Data Scientist | 0 | 8h | 100%
Identify Data Sources | Business | 0 | 40h | 100%
Identify Data Sources | Data Engineer | 0 | 40h | 100%
Identify Data Sources | Data Scientist | 0 | 40h | 100%
Identify Data Sources | DevOps | 0 | 40h | 100%
Identify Data Sources | Visualization | 0 | 40h | 100%
Identify Data Sources | IT Director | 0 | 40h | 100%
Data Sources Documented | Data Engineer | 0 | 0h | 100%
Data Sources Documented | Data Scientist | 0 | 0h | 100%
Data Sources Documented | DevOps | 0 | 0h | 100%
Data Dictionaries Delivered | Data Engineer | 0 | 0h | 100%
Data Dictionaries Delivered | Data Scientist | 0 | 0h | 100%
Data Dictionaries Delivered | DevOps | 0 | 0h | 100%
Charter Document Delivered | Data Scientist | 0 | 0h | 100%
Charter Document Delivered | Data Engineer | 0 | 0h | 100%
Charter Document Delivered | DevOps | 0 | 0h | 100%
Charter Document Delivered | IT Director | 0 | 0h | 100%
Ingest the data | Data Engineer | 0 | 24h | 100%
Explore the data | Data Engineer | 0 | 24h | 100%
Explore the data | Data Scientist | 0 | 24h | 100%
Explore the data | Front End Developer | 0 | 24h | 100%
Explore the data | Visualization | 0 | 24h | 100%
Set up data pipeline | Data Engineer | 0 | 8h | 100%
Set up data pipeline | DevOps | 0 | 8h | 100%
Deliver Data Quality Report | Data Engineer | 0 | 0h | 100%
Deliver Data Quality Report | Data Scientist | 0 | 0h | 100%
Deliver Data Quality Report | DevOps | 0 | 0h | 100%
Deliver a Solution Architecture | Data Scientist | 0 | 0h | 100%
Deliver a Solution Architecture | DevOps | 0 | 0h | 100%
Checkpoint Decision | Data Scientist | 0 | 0h | 100%
Checkpoint Decision | Business | 0 | 0h | 100%
Feature Engineering | Data Engineer | 0 | 8h | 100%
Feature Engineering | Data Scientist | 0 | 8h | 100%
Train Model | Data Scientist | 0 | 8h | 100%
Evaluate Model | Data Scientist | 0 | 8h | 100%
Define Feature Sets | Data Scientist | 0 | 8h | 100%
Create Model Report | Data Scientist | 0 | 8h | 100%
Checkpoint Decision | Data Scientist | 0 | 8h | 100%
Checkpoint Decision | IT Director | 0 | 8h | 100%
Checkpoint Decision | Business | 0 | 8h | 100%
Deployment | Data Engineer | 0 | 8h | 100%
Deployment | Data Scientist | 0 | 8h | 100%
Deployment | DevOps | 0 | 8h | 100%
Deployment | Front End Developer | 0 | 8h | 100%
Deployment | Tester | 0 | 8h | 100%
Deployment | Visualization | 0 | 8h | 100%
Operationalize the Model | DevOps | 0 | 8h | 100%
Operationalize the Model | Data Engineer | 0 | 8h | 100%
Operationalize the Model | Data Scientist | 0 | 8h | 100%
Operationalize the Model | Front End Developer | 0 | 8h | 100%
Operationalize the Model | Tester | 0 | 8h | 100%
Operationalize the Model | Visualization | 0 | 8h | 100%
Deliver status dashboard | Visualization | 0 | 0h | 100%
Deliver status dashboard | DevOps | 0 | 0h | 100%
Deliver status dashboard | Data Scientist | 0 | 0h | 100%
Deliver final modeling report | Data Scientist | 0 | 0h | 100%
Deliver final modeling report | DevOps | 0 | 0h | 100%
Deliver final modeling report | IT Director | 0 | 0h | 100%
Deliver Final solution architecture document | Data Scientist | 0 | 0h | 100%
Deliver Final solution architecture document | DevOps | 0 | 0h | 100%
System Validation | IT Director | 0 | 8h | 100%
System Validation | Data Scientist | 0 | 8h | 100%
System Validation | Tester | 0 | 8h | 100%
System Validation | DevOps | 0 | 8h | 100%
Project Handoff | IT Director | 0 | 8h | 100%